## Implementation Status
NIDP — Implementation Status as of 2026-05-27
Component | Category | Status | Notes | Owner / Next Action
TimescaleDB (port 5433) | Infrastructure | ✅ LIVE | 55+ migrations, nidp schema, hypertables | —
PostgreSQL replica (port 5432) | Infrastructure | ✅ LIVE | Staging replica on nidp-postgres-staging | —
Redis cache | Infrastructure | ✅ LIVE | nidp-redis container | —
Redpanda event bus | Infrastructure | ✅ LIVE | nidp-redpanda container (local dev only) | Promote to prod VM
MinIO object storage | Infrastructure | ✅ LIVE | nidp-minio container | —
Prometheus + Grafana | Observability | ✅ LIVE | data.niveshcopilot.com/grafana — feed-schedule + job-health | —
NSE/BSE price feed (OHLCV) | Data Feed | ✅ LIVE | Daily, 13 Cloud Run ingesters | —
NSE/BSE announcement pipeline (S4) | Data Feed | ✅ LIVE | Classifier → pgvector, live since 2026-05-07 | —
S5 embedder | Data Feed | 🔄 IN PROGRESS | Week 2 — vector embeddings for announcements | Complete S5 Week 2
TrueData live-feed trial | Data Feed | 🔄 IN PROGRESS | Validation-only trial through 2026-05-14 | Evaluate productionisation
NSE Integrated XBRL parser | Data Feed | ✅ LIVE | Full P&L + balance sheet from _WEB.xml | —
Screener.in quarterly P&L parser | Data Feed | ✅ LIVE | Event-driven on result announcement days | —
Screener.in balance sheet parser | Data Feed | ✅ LIVE | Wired 2026-05-27 — equity capital, reserves, borrowings | —
Screener.in annual P&L parser | Data Feed | ✅ LIVE | Wired 2026-05-27 — 9-year revenue + PAT history (NEW) | —
Screener.in shareholding parser | Data Feed | ✅ LIVE | Wired 2026-05-27 — promoter, FII, DII per quarter | —
Nifty 500 historical backfill | Data Feed | 🔄 IN PROGRESS | 213/504 done (2026-05-27); 271 in progress | Complete resume run
V3 scoring engine | Analytics | ✅ LIVE | Quality + Health scores, daily cron | Wire to cron post-backfill
populate_stock_features_extended | Analytics | ✅ LIVE | ROE, D/E, market cap, promoter from financials | Add to daily cron
populate_stock_features_v3 | Analytics | ✅ LIVE | 3Y CAGRs, margin trend, debt trend | Add to daily cron
exception_queue / DQ dashboard | Observability | ✅ LIVE | Feed failures surfaced in admin console | —
job_log | Observability | ✅ LIVE | Per-run status + row counts | —
Feed registry (feed_registry table) | Infrastructure | ❌ NOT BUILT | Planned: SLA tracking, retry policy, replay eligibility | Phase 1
Replay engine | Infrastructure | ❌ NOT BUILT | Planned: re-derive from raw MinIO archives | Phase 1
PostgreSQL HA / WAL replication | Infrastructure | ❌ NOT BUILT | Single-point-of-failure risk on nidp-stack-vm | Phase 1
TimescaleDB continuous aggregates | Analytics | ❌ NOT BUILT | Precompute rolling MAs, factor summaries | Phase 2
Parquet export to MinIO | Analytics | ❌ NOT BUILT | Archive stock_features_daily + nse_financials_quarterly | Phase 2
DuckDB analytics layer | Analytics | ❌ NOT BUILT | Backtesting + AI dataset generation on Parquet | Phase 2
AMC scrapers (mf_holdings) | Data Feed | ❌ BROKEN | 10 AMC sites all 404 / changed URL; blocks 4 MF primitives | Fix URLs — P1
earnings_surprise_pct source | Data Feed | ❌ MISSING | Needs consensus EPS estimates — no source identified yet | Evaluate options — P1

## Primitive Coverage
V3 Scoring — Primitive Coverage (Nifty 500)
Primitive | Score Type | Weight | Coverage Before | Coverage After (213 symbols) | Expected After Full Backfill | Blocker / Notes
roe_pct | Quality | 25% | 0% | ~42% | ~85%+ | Needs equity_share_capital_cr — now flowing from Screener BS
debt_to_equity | Quality | 15% | 0% | ~42% | ~85%+ | Needs total_equity_cr + borrowings — now flowing
eps_growth_3y_cagr_pct | Quality | 20% | 91% | 91% | 91% | Covered by NSE XBRL backfill
promoter_pct | Quality | 10% | 9% | ~41% | ~85%+ | Now from Screener shareholding section
market_cap_bucket | Quality | 10% | 0% | ~43% | ~85%+ | Needs equity_share_capital_cr + face_value + close
earnings_consistency | Quality | 20% | 93% | 93% | 93% | Covered by NSE XBRL backfill
revenue_growth_3y_cagr | Health | 25% | 0% | ~23% | ~60%+ | Needs 3 years annual revenue — Screener #profit-loss (NEW)
profit_margin_trend | Health | 20% | 0% | ~36% | ~70%+ | Needs annual PAT + revenue trend — now flowing
debt_trend | Health | 15% | 0% | ~35% | ~70%+ | Needs annual borrowings trend — now flowing
earnings_surprise_pct | Health | 15% | 0% | 0% | 0% | ❌ Needs consensus EPS estimates — no source yet
volatility_1y_pct | Health | 10% | 100% | 100% | 100% | From daily price data
dividend_yield_pct | Health | 5% | 100% | 100% | 100% | From dividend announcements + price

## Remaining Tasks
NIDP — Remaining Tasks (Prioritised)
# | Priority | Task | Impact | Effort | Notes / Dependencies
1 | P0 | Resume Screener.in backfill — 271 remaining Nifty 500 symbols | Completes balance sheet + P&L + shareholding coverage to ~85% | S | Running now (byqi8wqvj). Re-run without --force after rate limit resets
2 | P0 | Re-run populate_stock_features_extended + v3 + scores after backfill | Primitive coverage goes from 42% → 85%+ for ROE/D&E/promoter | S | Will auto-chain after backfill completes
3 | P0 | Fix BAJAJFINSV slug in _SCREENER_SLUG_MAP | Recovers 1 Nifty 50 symbol currently returning not_found | XS | Add 'BAJAJFINSV': 'BAJAJ-FINSERV' to ir_scraper.py
4 | P0 | Add populate_stock_features_extended + v3_scores_engine to daily cron | Without cron entry, features go stale after each trading day | S | NIDP VM crontab — add after price feed cron entry
5 | P1 | Fix AMC scrapers (mf_holdings + mf_disclosure_snapshot) | Unblocks 4 MF scoring primitives currently at 0% | M | 10 AMC sites changed URL; scrape new IR pages for each
6 | P1 | Identify earnings_surprise_pct source | Last Health primitive at 0%; worth 15% of health score | M | Evaluate: NSE XBRL comparator, screener ratios, Trendlyne API
7 | P1 | Screener.in session cookie rotation alert | Cookie expires 2026-06; backfill will silently fail after that | S | Add expiry check to backfill startup; alert via exception_queue
8 | P1 | Screener.in off-peak scheduling (2–5 AM IST) | Avoids rate limits on weekly Nifty 500 refresh | S | Change cron schedule; add jitter between requests
9 | P2 | Score band calibration | Validates scores are not clustering near 50 (null fallback) | M | Run after full backfill; histogram quality_score distribution
10 | P2 | Ranking gate — suppress scores below 50% coverage | Prevents misleading scores from being surfaced in UI | S | Add quality_coverage_pct < 50 filter in V3 API response
11 | P2 | earnings_consistency_score methodology review | Verify loss-making companies handled correctly | S | Check EPS sign logic for NBFCs, startups, cyclicals
12 | P2 | short_term_debt_cr gap | Screener lumps borrowings; affects D/E precision for NBFCs | M | Supplement from NSE XBRL balance sheet or Trendlyne
13 | P2 | NIDP→Copilot ownership map cleanup | equity_pct/beta computed in both NIDP and Copilot (duplication) | M | Wire Copilot to call NIDP snapshot endpoint instead
14 | P3 | Feed registry (feed_registry + feed_execution tables) | SLA tracking, retry policy, replay eligibility per feed | L | Phase 1 infrastructure foundation
15 | P3 | Replay engine | Re-derive primitives + scores from raw MinIO archives | L | Depends on feed registry + MinIO raw layer
16 | P3 | PostgreSQL HA — WAL replication | Eliminates single-point-of-failure on nidp-stack-vm | L | Phase 1 — needs second VM or managed PG
17 | P3 | TimescaleDB continuous aggregates | Precompute 20/50/200 day rolling averages | M | Phase 2 — reduces query time for technical indicators
18 | P3 | Parquet export to MinIO + DuckDB | Enables backtesting + AI dataset generation | L | Phase 2 — archive stock_features_daily + nse_financials_quarterly

## Feed Architecture
NIDP — Feed Architecture & Data Sources
Feed / Source | Type | Covers | Primitives Fed | Status | Limitation
NSE XBRL backfill (nse_xbrl_backfill) | XBRL XML | 458/504 Nifty 500 | eps_basic, ebitda_cr, finance_costs | ✅ LIVE | Only EPS + EBITDA — no revenue, no balance sheet
NSE Integrated XBRL (_WEB.xml) | XBRL XML | ~458 symbols (event-driven) | Full P&L + balance sheet (equity, borrowings) | ✅ LIVE | Only fires on result announcement day
Screener.in #quarters | HTML scrape | ~504 symbols | revenue, PAT, EPS, EBITDA (quarterly) | ✅ LIVE | Rate-limited; requires session cookie
Screener.in #balance-sheet (NEW) | HTML scrape | ~504 symbols | equity_share_capital, total_equity, borrowings (annual) | ✅ LIVE | Annual only — no quarterly balance sheet
Screener.in #profit-loss (NEW) | HTML scrape | ~504 symbols | revenue_growth_3y_cagr, profit_margin_trend (annual) | ✅ LIVE | 3-year window needed for CAGR computation
Screener.in #shareholding (NEW) | HTML scrape | ~504 symbols | promoter_pct, FII, DII (quarterly) | ✅ LIVE | —
NSE/BSE price feed | API | ~2500 symbols | volatility_1y, dividend_yield, market_cap | ✅ LIVE | —
NSE/BSE announcements (S4) | API + classifier | All listed | earnings_consistency (via EPS history) | ✅ LIVE | —
AMC scrapers (mf_holdings) | HTML scrape | 10 AMCs → Nifty 500 MF holdings | 4 MF scoring primitives | ❌ BROKEN | All 10 AMC IR pages changed URL
Consensus EPS estimates | TBD | TBD | earnings_surprise_pct (15% Health weight) | ❌ NO SOURCE | Evaluate: Trendlyne, NSE XBRL comparator, screener ratios