## Master Feed Registry
NIDP — Master Data Feed Registry ¦ as of 2026-05-27
Feed Name | Domain | Source | Frequency | Raw Layer | Status | Downstream Tables | Gap / Issue
NSE OHLCV Price Feed | Equity Price | NSE API | Daily | MinIO | ✅ LIVE | stock_price_daily, stock_features_daily | —
BSE OHLCV Price Feed | Equity Price | BSE API | Daily | MinIO | ✅ LIVE | stock_price_daily | —
NSE Corporate Announcements | Equity Events | NSE Corporate API | Real-time | MinIO | ✅ LIVE | announcements, event_calendar, documents (pgvec) | —
BSE Corporate Announcements | Equity Events | BSE XBRL API | Real-time | MinIO | ✅ LIVE | announcements, event_calendar | —
NSE Integrated XBRL (_WEB.xml) | Equity Financials | NSE nsearchives | Event | — | ✅ LIVE | nse_financials_quarterly | Only fires on result day
Screener.in — Quarterly P&L | Equity Financials | Screener.in HTML | Event | raw_data JSONB | ✅ LIVE | nse_financials_quarterly | Rate-limited; manual session cookie
Screener.in — Balance Sheet | Equity Financials | Screener.in HTML #balance-sheet | Weekly | raw_data JSONB | ✅ LIVE | nse_financials_quarterly (equity, borrowings) | Annual only — no intra-year B/S
Screener.in — Annual P&L | Equity Financials | Screener.in HTML #profit-loss | Weekly | raw_data JSONB | ✅ LIVE | nse_financials_quarterly (annual rows) | New as of 2026-05-27
Screener.in — Shareholding | Equity Ownership | Screener.in HTML #shareholding | Weekly | raw_data JSONB | ✅ LIVE | shareholding_pattern | New as of 2026-05-27
NSE XBRL Backfill | Equity Financials | NSE XBRL Comparator API | Backfill | — | ✅ LIVE | nse_financials_quarterly | Only EPS + EBITDA — no B/S, no revenue
NSE Index Constituents | Equity Reference | NSE Indices API | Daily | MinIO | ✅ LIVE | index_constituents | —
Company Master (symbol map) | Equity Reference | NSE Company Master | Weekly | MinIO | ✅ LIVE | security_master | —
TrueData Live Feed (trial) | Equity Price | TrueData WS API | Live | — | 🔄 IN PROGRESS | Validation only — not writing to prod tables | Trial through 2026-05-14; evaluate productionisation
S5 Embedder (announcements) | Equity Intelligence | pgvector + OpenAI | Event | — | 🔄 IN PROGRESS | documents (pgvector embeddings) | Week 2 in progress
AMC Holdings Scraper | MF Holdings | 10 AMC IR pages | Monthly | — | ❌ BROKEN | mf_holdings, mf_disclosure_snapshot | All 10 AMC sites 404/changed URL — blocks 4 MF primitives
MF NAV Feed | MF Price | AMFI API | Daily | MinIO | ✅ LIVE | mf_nav_daily | —
MF Scheme Master | MF Reference | AMFI API | Weekly | MinIO | ✅ LIVE | mf_scheme_master | —
Consensus EPS Estimates | Equity Financials | TBD | Quarterly | — | ❌ NO SOURCE | stock_features_daily (earnings_surprise_pct) | Needed for 15% Health weight primitive — evaluate Trendlyne / NSE XBRL

## Infrastructure Status
NIDP — Infrastructure & Platform Status
Component | Layer | VM / Host | Status | Phase Target | Notes
TimescaleDB (primary) | Storage / OLTP | nidp-stack-vm:5433 | ✅ LIVE | Foundation | 55+ migrations, hypertables, nidp schema
PostgreSQL replica | Storage / OLTP | nidp-stack-vm:5432 | ✅ LIVE | Foundation | Staging replica — not full HA yet
Redis | Cache | nidp-redis | ✅ LIVE | Foundation | Session cache, rate limiting
Redpanda | Event Streaming | nidp-redpanda | ✅ LIVE | Foundation | Running locally — topics defined but producers not fully wired
MinIO | Object Storage | nidp-minio | ✅ LIVE | Foundation | Raw file archive — OHLCV + announcements
Prometheus | Monitoring | nidp-prometheus | ✅ LIVE | Foundation | Scraping all containers
Grafana | Observability | nidp-grafana | ✅ LIVE | Foundation | data.niveshcopilot.com/grafana — feed + job health
PostgreSQL HA (WAL replication) | HA / DR | VM-2 (not built) | ❌ NOT BUILT | Phase 1 | Single point of failure — nidp-stack-vm
Redis replica | HA / DR | VM-2 (not built) | ❌ NOT BUILT | Phase 1 | AOF persistence only currently
Feed Registry tables | Operations | PostgreSQL | ❌ NOT BUILT | Phase 1 | feed_registry + feed_execution + feed_dependencies
Replay engine | Operations | Worker | ❌ NOT BUILT | Phase 1 | Re-derive from MinIO raw archives — no re-fetch needed
Quarantine / exception_queue | Operations | PostgreSQL | ✅ LIVE | Phase 1 | exception_queue table + DQ dashboard surfacing
HAProxy / Nginx LB | API HA | Both VMs | ❌ NOT BUILT | Phase 1 | Currently single API server
TimescaleDB continuous aggregates | Analytics | PostgreSQL | ❌ NOT BUILT | Phase 2 | Precompute rolling MAs, factor summaries
Parquet export to MinIO | Analytics | Cloud Run worker | ❌ NOT BUILT | Phase 2 | Archive stock_features_daily + nse_financials_quarterly
DuckDB analytics layer | Analytics | VM-2 worker | ❌ NOT BUILT | Phase 2 | Backtesting + AI dataset generation on Parquet
Schema drift detector | Intelligence | CI / Cloud Run | ❌ NOT BUILT | Phase 3 | Alert when upstream XBRL taxonomy or screener HTML changes
AI-assisted feed healing | Intelligence | LLM worker | ❌ NOT BUILT | Phase 3 | Auto-patch parsers when schema drifts

## Primitive Coverage
V3 Scoring — Primitive Coverage (Nifty 500, 2026-05-27)
Primitive | Score | Weight | Before | After (213 symbols) | After Full Backfill | Feed Source / Blocker
roe_pct | Quality | 25% | 0% | ~42% | ~85%+ | Screener #balance-sheet → equity_share_capital_cr (NEW)
debt_to_equity | Quality | 15% | 0% | ~42% | ~85%+ | Screener #balance-sheet → total_equity_cr + borrowings (NEW)
eps_growth_3y_cagr_pct | Quality | 20% | 91% | 91% | 91% | NSE XBRL backfill — EPS history
promoter_pct | Quality | 10% | 9% | ~41% | ~85%+ | Screener #shareholding (NEW)
market_cap_bucket | Quality | 10% | 0% | ~43% | ~85%+ | equity_share_capital_cr × close ÷ face_value
earnings_consistency | Quality | 20% | 93% | 93% | 93% | NSE XBRL backfill — EPS sign consistency
revenue_growth_3y_cagr | Health | 25% | 0% | ~23% | ~60%+ | Screener #profit-loss annual revenue (NEW)
profit_margin_trend | Health | 20% | 0% | ~36% | ~70%+ | Screener #profit-loss PAT ÷ revenue trend (NEW)
debt_trend | Health | 15% | 0% | ~35% | ~70%+ | Screener #balance-sheet borrowings trend (NEW)
earnings_surprise_pct | Health | 15% | 0% | 0% | 0% | ❌ No consensus estimates source identified yet
volatility_1y_pct | Health | 10% | 100% | 100% | 100% | NSE daily price feed
dividend_yield_pct | Health | 5% | 100% | 100% | 100% | NSE dividend announcements + price

## Remaining Tasks
NIDP — Remaining Tasks (Prioritised)
# | Pri | Task | Category | Impact | Effort | Notes / Dependencies
1 | P0 | Resume backfill — 271 remaining Nifty 500 symbols | Data Feed | Coverage 42%→85%+ for ROE/D&E/promoter | S | Running (byqi8wqvj) — auto-chain feature recompute after
2 | P0 | Add feature compute + v3_scores_engine to daily cron | Operations | Features go stale without cron; scores drift | S | NIDP VM crontab — after price feed entry
3 | P0 | Fix BAJAJFINSV slug (_SCREENER_SLUG_MAP) | Data Feed | Recovers 1 Nifty 50 symbol (not_found) | XS | Add 'BAJAJFINSV': 'BAJAJ-FINSERV' in ir_scraper.py
4 | P1 | Fix AMC scrapers (mf_holdings + mf_disclosure_snapshot) | Data Feed | Unblocks 4 MF scoring primitives at 0% | M | 10 AMC sites changed URL — scrape new IR pages
5 | P1 | Identify earnings_surprise_pct source | Data Feed | Last Health primitive at 0% (15% weight) | M | Evaluate Trendlyne API, NSE XBRL comparator, screener ratios
6 | P1 | Screener cookie expiry alert | Operations | Backfill silently fails after cookie expires | S | Cookie expires ~2026-06; add check in backfill startup
7 | P1 | Off-peak Screener scheduling (2–5 AM IST) | Operations | Avoids rate limits on weekly Nifty 500 refresh | S | Change cron time + add request jitter
8 | P1 | Wire Redpanda producers for feed events | Infrastructure | Enables event-driven downstream processing | M | Producers defined but not wired to ingesters
9 | P2 | Score band calibration + ranking gate | Analytics | Prevent misleading scores from surfacing | M | Histogram quality_score; suppress if coverage < 50%
10 | P2 | earnings_consistency review (loss-making stocks) | Analytics | Fix scoring for NBFCs, cyclicals, startups | S | EPS sign logic edge cases
11 | P2 | short_term_debt_cr gap for NBFCs/banks | Data Feed | Affects D/E precision for financial stocks | M | Screener lumps borrowings; supplement from XBRL
12 | P2 | NIDP→Copilot ownership map cleanup | Architecture | Eliminate equity_pct/beta duplication | M | Wire Copilot to NIDP snapshot endpoint /v1/intelligence/portfolio/{id}/snapshot
13 | P2 | Consolidation/Exit scoring wire-up | Analytics | winner_pick_pending=True blocking rec display | M | Depends on NIDP data-lake green signal
14 | P3 | Feed registry (feed_registry + feed_execution tables) | Infrastructure | SLA tracking, retry policy, replay eligibility | L | Phase 1 foundation prerequisite
15 | P3 | Replay engine | Infrastructure | Re-derive from MinIO raw without re-fetching | L | Depends on feed registry + MinIO raw layer
16 | P3 | PostgreSQL HA — WAL replication | Infrastructure | Eliminate single-point-of-failure | L | nidp-stack-vm currently unprotected
17 | P3 | TimescaleDB continuous aggregates | Analytics | Faster rolling MA queries | M | Phase 2
18 | P3 | Parquet export + DuckDB analytics | Analytics | Backtesting + AI dataset generation | L | Archive stock_features_daily + nse_financials_quarterly
19 | P3 | Schema drift detector + AI-assisted healing | Intelligence | Auto-detect + patch parser breakage | XL | Phase 3 — requires feed registry as base

## Two-VM Architecture
NIDP — Two-VM Target Architecture & Current Gaps
Component | Target VM | Responsibility | Current State | Gap | Phase | Priority
PostgreSQL / TimescaleDB primary | VM-1 | OLTP, time-series storage | ✅ Running on nidp-stack-vm | Not HA — single VM | Phase 1 | P1
Redis primary | VM-1 | Session cache, rate limit | ✅ Running on nidp-stack-vm | No AOF persistence configured | Phase 1 | P1
API Layer (FastAPI) | VM-1 | DaaS API, NIDP query API | ✅ Running on nidp-stack-vm | Single server — no LB | Phase 1 | P2
HAProxy / Nginx | VM-1 | API load balancing across VMs | ❌ Not built | No load balancing at all | Phase 1 | P2
Prometheus | VM-1 | Metrics scraping | ✅ Running | — | — | —
Grafana | VM-1 | Visualisation + alerting | ✅ Running | — | — | —
Feed ingestion workers | VM-2 | Cloud Run ingesters (13 feeds) | ✅ Running on Cloud Run | Cloud Run not VM-2 — OK for now | Phase 2 | P3
Parser workers | VM-2 | XBRL, HTML, PDF parsers | ✅ Running in-process | Single-threaded — no queue parallelism | Phase 2 | P3
Redpanda | VM-2 | Event streaming between components | ✅ Container (not yet wired) | Producers not wired to ingesters | Phase 1 | P1
MinIO | VM-2 | Immutable raw layer (object storage) | ✅ Container (not fully used) | Raw files not all archived yet | Phase 1 | P1
PostgreSQL replica | VM-2 | WAL streaming replica for HA | ❌ Not built (staging only) | Single point of failure | Phase 1 | P1
Redis replica | VM-2 | Standby for HA | ❌ Not built | — | Phase 1 | P2
Replay engine | VM-2 | Re-derive from raw MinIO archives | ❌ Not built | No replay capability at all | Phase 1 | P2
DuckDB analytics | VM-2 | Historical analytics on Parquet | ❌ Not built | No Parquet archives yet | Phase 2 | P3
Parquet archival worker | VM-2 | Export time-series to MinIO as Parquet | ❌ Not built | — | Phase 2 | P3